## Financial Report_SL
| Financial Report 1566-ICREEC Project (Samlout) Date: January to September 2016 | [15 empty] | Funder
Educo
Activity | Budget 2016 | Expenditure 2016 | [11 empty] | Total Expenses | Balance | % Spent | % Balance | Remark
|  | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Objective 1. | 18140 | 458.27 | 1444.61 | 475.86 | 691.85 | 507.81 | 1078.05 |  | 1438.2 | 1166.13 |  |  |  | 7260.78 | 10879.22 | 40.03% | 59.97%
Objective 2. | 11310 | 174.41 | 706.4 | 855.06 | 1067.37 | 1125.69 | 1077.45 |  | 114.81 | 2131.06 |  |  |  | 7252.25 | 4057.75 | 64.12% | 35.88%
Objective 3. | 7070.5 | 460.31 | 568.59 | 415.02 | 182.13 | 816.91 | 238.48 | 24.3 | 159.52 | 338.65 |  |  |  | 3203.91 | 3866.59 | 45.31% | 54.69%
Objective 4. | 21433 | 670.14 | 1298.66 | 869.58 | 263.47 | 441.07 | 1651.75 | 824.01 | 969.18 | 395.7 |  |  |  | 7383.56 | 14049.44 | 34.45% | 65.55%
Objective 5. | 2224 | Expenditure 2016 Jan: 0; Expenditure 2016 Feb: 86.76; Expenditure 2016 Mar: 57; Expenditure 2016 Apr: 505.64; Expenditure 2016 May: 77; Expenditure 2016 Jun: 316.88; Expenditure 2016 Aug: 26 | 1069.28 | 1154.72 | 48.08% | 51.92%
Project Salary | 27680 | 2198.5 | 2129.37 | 2125.71 | 2434.39 | 2228.6 | 2251.19 |  | 4424.25 | 2190 |  |  |  | 19982.01 | 7697.99 | 72.19% | 27.81%
Program Support | 10560 | 627.47 | 655.44 | 879.21 | 1086.71 | 647.37 | 698.12 | 32.26 | 1690.28 | 405.17 |  |  |  | 6722.03 | 3837.97 | 63.66% | 36.34%
Project Total | 98417.5 | 4589.1 | 6889.83 | 5677.44 | 6231.56 | 5844.45 | 7311.92 | 880.57 | 8822.24 | 6626.71 | 0 | 0 | 0 | 52873.82 | 45543.68 | 53.72% | 46.28%
Objectives:
1 . To increase accessibility of Child Friendly Schools in collaboration with Communities so that all eligible children can enrol and attend school.
2. To facilitate in collaboration with the DOE sustainable improvement in the quality of teaching as measured by the MoEYS/ CFS dimensions
3. To facilitate in collaboration with P/DOE and SSCs sustainable improvement in the standard of school management in accordance with CFS standards.
4. To increase parents, teachers and children’s capacity, to ensure Child Rights through the provision of training and other support
5. To build KHEN’s capacity in applying a Rights based approach to project activities

## Financial Report _RKK
| Financial Report 1432-IPEQCOS Project (RKK) Date: January to June 2016 | [15 empty] | Funder
Educo
Activity | Budget 2016 | Expenditure 2016 | [11 empty] | Total Expenses | Balance | % Spent | % Balance | Remark
|  | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Objective 1. | 2260 | Expenditure 2016 Jan: 364.21; Expenditure 2016 Feb: 204.15; Expenditure 2016 Mar: 249.54; Expenditure 2016 Apr: 251.22; Expenditure 2016 May: 232.94; Expenditure 2016 Jun: 831.96 | 2134.02 | 125.98 | 94.43% | 5.574%
Objective 2. | 1134 | Expenditure 2016 Jan: 160.18; Expenditure 2016 Feb: 141.96; Expenditure 2016 Mar: 112.59; Expenditure 2016 Apr: 96.08; Expenditure 2016 May: 124.45; Expenditure 2016 Jun: 693.41 | 1328.67 | -194.67 | 117.2% | -17.17%
Objective 3. | 1120 | Expenditure 2016 Jan: 217; Expenditure 2016 Feb: 171.72; Expenditure 2016 Mar: 184.99; Expenditure 2016 Apr: 126.81; Expenditure 2016 May: 184.4; Expenditure 2016 Jun: 313.97 | 1198.89 | -78.89 | 107% | -7.044%
Objective 4. | 9662 | Expenditure 2016 Jan: 213.5; Expenditure 2016 Feb: 326; Expenditure 2016 Mar: 71.51; Expenditure 2016 Apr: 2270.83; Expenditure 2016 May: 63; Expenditure 2016 Jun: 476 | 3420.84 | 6241.16 | 35.41% | 64.59%
Project Salary | 13722 | Expenditure 2016 Jan: 2425; Expenditure 2016 Feb: 2345; Expenditure 2016 Mar: 2345; Expenditure 2016 Apr: 2345; Expenditure 2016 May: 2345; Expenditure 2016 Jun: 2345 | 14150 | -428 | 103.1% | -3.119%
Program Support | 4100 | Expenditure 2016 Jan: 579.37; Expenditure 2016 Feb: 640.55; Expenditure 2016 Mar: 833.83; Expenditure 2016 Apr: 574.56; Expenditure 2016 May: 726.43; Expenditure 2016 Jun: 716.51 | 4071.25 | 28.75 | 99.3% | 0.7012%
Project Total | 31998 | Expenditure 2016 Jan: 3959.26; Expenditure 2016 Feb: 3829.38; Expenditure 2016 Mar: 3797.46; Expenditure 2016 Apr: 5664.5; Expenditure 2016 May: 3676.22; Expenditure 2016 Jun: 5376.85 | 26303.67 | 5694.33 | 82.2% | 17.8%
Objectives:
1. Child Rights to fulfil their potentials through quality education is met.
2. Teachers’ proficiency is enhanced and nurtured.
3. School based management and its facilities have been promoted to a safe learning environment.
4. Community is obliged as the second duty bearer to the rights of their children.

## Financial Report_Getxo
| Financial Report 1617-Getxo Project Date: January to September 2016 | [15 empty] | Funder
Educo
Activity | Budget 2016 | Expenditure 2016 | [11 empty] | Total Expenses | Balance | % Spent | % Balance | Remark
|  | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Objective 1. | 17995.45 | 236.38 | 435.94 | 661.06 | 21.12 | 6473.72 | 2973.13 | 2930.59 | 0 | 157.5 |  |  |  | 13889.44 | 4106.01 | 77.18% | 22.82%
Objective 2. | 2650 | 79.81 | 95.75 | 147.48 | 241.05 | 117.55 | 428.48 | 279.41 | 140.28 | 153.39 |  |  |  | 1683.2 | 966.8 | 63.52% | 36.48%
Project Salary | 4404 | 366.99 | 733.98 | 366.99 | 367 | 367 | 367 | 367 | 367 | 367 |  |  |  | 3669.96 | 734.04 | 83.33% | 16.67%
Program Support | 1150 | 66.74 | 0 | 32.48 | 104.07 | 142.08 | 45.36 | 77.6 | 421.41 | 47.52 |  |  |  | 937.26 | 212.74 | 81.5% | 18.5%
Project Total | 26199.45 | 749.92 | 1265.67 | 1208.01 | 733.24 | 7100.35 | 3813.97 | 3654.6 | 928.69 | 725.41 | 0 | 0 | 0 | 20179.86 | 6019.59 | 77.02% | 22.98%
Objectives:
1. Infrastructures are improved and the community’s capacity to maintain and manage water supply systems in 4 community schools are reinforced with respect to the standards of Unicef's WASH program (Water, Sanitation and Hygiene).
2. The educational community's mechanisms and capacities are strengthened with respect to the management of water resources and systems and the health and hygiene practices in 8 community schools in Rukhakiri and Samlout are improved.

## Financial Report_CDIDF
Financial Report 5-CDIDF Project Date: January to September 2016 | [16 empty] | Funder:
Australian Aid through Unicef
Activity | Budget 2016 | Expenditure 2016 | [11 empty] | Total Expenses | Balance | % Spent | % Balance | Remark
|  | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Objective 1. | 3290 | 21.5 | 177.37 | 797.95 | 66.69 | 387.69 | 573.83 | 122.37 | 250.21 | 302.17 |  |  |  | 2699.78 | 590.22 | 82.06% | 17.94%
Objective 2. | 5400 | 396.34 | 335.32 | 374.43 | 316.25 | 777.58 | 606.26 | 403.04 | 873.23 | 340.82 |  |  |  | 4423.27 | 976.73 | 81.91% | 18.09%
Objective 3. | 5198 | 227.11 | 217.56 | 1101.36 | 144.97 | 630.29 | 1373.97 | 589 | 767.99 | 293.06 |  |  |  | 5345.31 | -147.31 | 102.8% | -2.834%
Objective 4. | 730 | 0 | 74.63 | 106.5 | 171.47 | 72.4 | 63.38 | 0 | 0 | 166.4 |  |  |  | 654.78 | 75.22 | 89.7% | 10.3%
Project Salary | 4800 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 |  |  |  | 3600 | 1200 | 75% | 25%
Program Support | 3468 | 285.57 | 280.25 | 299.77 | 313.23 | 307.58 | 272 | 324.74 | 292.75 | 274 |  |  |  | 2649.89 | 818.11 | 76.41% | 23.59%
Project Total | 22886 | 1330.52 | 1485.13 | 3080.01 | 1412.61 | 2575.54 | 3289.44 | 1839.15 | 2584.18 | 1776.45 | 0 | 0 | 0 | 19373.03 | 3512.97 | 84.65% | 15.35%
Objectives:
1. For all identified Children with Disabilities, in 4 target clusters to access relevant education by 2016.
2. To develop 20 school environments and their teaching &amp; school management practices to meet the needs of Children with Disabilities (as per Child Friendly School Standards) in 4 target clusters by 2016.
3. To build sustainable community/parental capacity in providing appropriate care & support for children with disabilities and advocating effectively for their needs, in 4 communes by 2016.
4. To improve the capacity of KHEN to appropriately, effectively, and sustainably support the Rights of Children and Adults with Disabilities by 2016.

## Financial Report Global
Global Financial Report Date: January to September 2016
Activity | Budget 2016 | Expenditure 2016 | [11 empty] | Total Expenses | Balance | % Spent | % Balance
|  | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
1566-ICREEC Project (Samlout) | 60177.5 | 1763.13 | 4105.02 | 2672.52 | 2710.46 | 2968.48 | 4362.61 | 848.31 | 2707.71 | 4031.54 | 0 | 0 | 0 | 26169.78 | 34007.72 | 43.49% | 56.51%
1432-IPEQCOS Project (RKK) | 14176 | 954.89 | 843.83 | 618.63 | 2744.94 | 604.79 | 2315.34 | 0 | 0 | 0 | 0 | 0 | 0 | 8082.42 | 6093.58 | 57.01% | 42.99%
5-CDIDF Project | 14618 | 644.95 | 804.88 | 2380.24 | 699.38 | 1867.96 | 2617.44 | 1114.41 | 1891.43 | 1102.45 | 0 | 0 | 0 | 13123.14 | 1494.86 | 89.77% | 10.23%
1617-GETXO Project | 20645.45 | 316.19 | 531.69 | 808.54 | 262.17 | 6591.27 | 3401.61 | 3210 | 140.28 | 310.89 | 0 | 0 | 0 | 15572.64 | 5072.81 | 75.43% | 24.57%
II.Direct Project Salary | 50606 | 5390.49 | 4874.37 | 4870.71 | 5179.39 | 4973.6 | 4996.19 | 400 | 4824.25 | 2590 | 0 | 0 | 0 | 38099 | 12507 | 75.29% | 24.71%
III.Program Support | 19278 | 1559.15 | 1576.24 | 2012.81 | 1974.5 | 1681.38 | 1686.63 | 357 | 1983.03 | 679.17 | 0 | 0 | 0 | 13509.91 | 5768.09 | 70.08% | 29.92%
Project Total | 179500.95 | 10628.8 | 12736.03 | 13363.45 | 13570.84 | 18687.48 | 19379.82 | 5929.72 | 11546.7 | 8714.05 | 0 | 0 | 0 | 114556.89 | 64944.06 | 63.82% | 36.18%

## Expenditure
Global Financial Report Date: January to September 2016
Activity | Expenditure January to September 2016 | [11 empty] | Total Expenses
| Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Direct Cost | 9069.65 | 11159.79 | 11350.64 | 11596.34 | 17006.1 | 17693.19 | 5572.72 | 9563.67 | 8034.88 |  |  |  | 101046.98
Program Support (Indirect Cost) | 1559.15 | 1576.24 | 2012.81 | 1974.5 | 1681.38 | 1686.63 | 357 | 1983.03 | 679.17 |  |  |  | 13509.91
Project Total | 10628.8 | 12736.03 | 13363.45 | 13570.84 | 18687.48 | 19379.82 | 5929.72 | 11546.7 | 8714.05 | 0 | 0 | 0 | 114556.89